## Backlog
Key | Epic | User Story | Description | Acceptance Criteria | Story Points | Priority | Status | Assignee | Branch | Sprint | Labels
TR_0 |  |  | Create Documentation | Create Srs ,JiraTask Sheet ,Presentation ,Final Report | 4 | High | To Do | Vansh | document-setup | Sprint 0 | docs
TR-1 | Project Setup | Initialize Flask Project | Create env and structure | Project runs locally | 3 | High | To Do | Vansh | feature/setup-flask | Sprint 1 | backend
TR-2 | Model Integration | Load Translation Model | Integrate Helsinki NLP model | Model loads without error | 8 | High | To Do | Vansh | feature/model-integration | Sprint 1 | ai,nlp
TR-3 | API | Create Translate Endpoint | POST API returns Hindi text | Valid JSON response | 5 | High | To Do | Rahul | feature/translation-api | Sprint 1 | backend,api
TR-4 | Validation | Handle Invalid Inputs | Empty input handling | Returns validation message | 3 | Medium | To Do | Rahul | feature/input-validation | Sprint 1 | backend
TR-5 | Frontend | Create UI Layout | Textbox and button | Responsive page | 5 | Medium | To Do | Priya | feature/frontend-ui | Sprint 2 | frontend
TR-6 | Frontend | Display Output | Show translated text | Hindi text visible | 3 | Medium | To Do | Priya | feature/output-display | Sprint 2 | frontend
TR-7 | UX | Loading Indicator | Add spinner | Visible during request | 2 | Low | To Do | Priya | feature/loading-spinner | Sprint 2 | frontend,ux
TR-8 | Error Handling | Server Error Responses | Graceful error message | No crashes | 3 | High | To Do | Vansh | feature/error-handling | Sprint 2 | backend
TR-9 | Deployment | Deploy on Render | Setup build and start | Live URL accessible | 5 | High | To Do | Aman | feature/deploy-render | Sprint 3 | devops
TR-10 | Testing | Functional Testing | Test translation accuracy | All cases pass | 5 | Medium | To Do | Aman | feature/testing | Sprint 3 | qa
TR-11 | Optimization | Reduce Latency | Improve response time | <3s response | 8 | Medium | To Do | Vansh | feature/performance | Sprint 3 | ai,performance
TR-12 | Documentation | Prepare Docs | README + SRS | Complete docs | 2 | Low | To Do | Rahul | feature/documentation | Sprint 3 | docs